Core Responsibilities Project manager

- Technical Competence: Evaluates technical feasibility, architectural choices, and technical risks to make informed decisions without micromanaging specialists.

- Planning & Organizing: Defines scope, constructs the Work Breakdown Structure (WBS), estimates effort, sets schedules, and allocates resources.

- Leadership & Team Management: Provides direction, builds trust, handles team conflicts, and creates an environment where issues can be discussed openly.

- Communication: Serves as the central link connecting customers, senior management, developers, testers, analysts, and vendors.

- Risk Management: Identifies potential uncertainties early, calculates risk exposure, develops response plans, and monitors risk triggers.

- Problem-Solving & Decision-Making: Evaluates trade-offs between cost, time, and quality, focusing on resolving underlying root causes rather than treating symptoms.

- Negotiation & Adaptability: Negotiates realistic compromises when client feature requests conflict with deadlines, and adapts plans as requirements change.

- Ethical Responsibility: Maintains complete honesty regarding project status, schedule delays, costs, risks, and technical limitations.

Good PM vs. Successful Software PM

- Good Project Manager: Demonstrates standard administrative practices like planning, organizing, communicating, and controlling.

- Successful Software Project Manager: Combines administrative management with technical understanding, leadership, adaptability, and proactive risk management to achieve objectives in a changing software environment.

BEST OF LUCK 🌻

Software Project Management

6 Primary Effort Estimation Techniques

- Expert Judgment: Estimating effort based on personal background, domain experience, and historical memory.

- Estimating by Analogy: Comparing the proposed project to similar past completed projects.

- Top-Down Estimating: Estimating total project effort first and dividing it among major development phases.

- Bottom-Up Estimating: Estimating individual WBS work packages separately and summing them up.

- Function Point Analysis (FPA): Sizing software based on user functionality (Inputs, Outputs, Inquiries, Internal Files, External Interfaces) independent of programming language.

- COCOMO Model: Algorithmic model estimating effort in Person-Months based on software size in KSLOC.

Software Project Scheduling

WBS Rules & Decomposition Styles

- 100% Rule: The WBS must encompass 100% of the work defined by the project scope—no extra work included and no required work omitted8.

- Mutual Exclusion: Each WBS element must represent distinct work to avoid double-counting tasks9.

- Work Package: The lowest WBS level where work can be estimated, scheduled, assigned, and monitored9.

- Product-Oriented WBS: Decomposes work by major software components (e.g., User Interface, Database, Server)9.

- Process-Oriented WBS: Decomposes work by development phases (e.g., Requirements, Design, Coding, Testing)910.

- Hybrid WBS: Combines product deliverables at one level and process activities at another10.

PDM / AON Dependency Types

- Finish-to-Start (FS): Successor task cannot start until the predecessor task finishes1112.

- Start-to-Start (SS): Successor task cannot start until the predecessor task starts11.

- Finish-to-Finish (FF): Successor task cannot finish until the predecessor task finishes11.

- Start-to-Finish (SF): Successor task cannot finish until the predecessor task starts11.

4 Categories of Dependencies

- Mandatory Dependency: Hard logic inherent in the nature of the work (e.g., code must be written before it can be tested)1213.

- Discretionary Dependency: Soft logic defined by the project team based on preference or best practices13.

- External Dependency: Precedence relationship driven by external non-project entities (e.g., government regulations)1314.

- Internal Dependency: Precedence relationship between internal project activities14.

Schedule Compression Techniques

- Project Crashing: Adding extra resources to critical path activities to shorten duration at the expense of higher costs1516.

- Fast Tracking: Executing critical tasks in parallel that were originally planned sequentially, increasing the risk of rework16.

PERT vs. CPM

- Critical Path Method (CPM): Deterministic scheduling technique using a single time estimate to identify the longest sequence of dependent tasks with zero float17more_horiz.

- Program Evaluation and Review Technique (PERT): Probabilistic scheduling technique using 3 time estimates (Optimistic $a$, Most Likely $m$, Pessimistic $b$) for projects with uncertain activity durations15more_horiz.

4 Key Project Evaluation Questions

- Is it strategically valuable?: Determines alignment with long-term business goals and competitive position.

- Is it technically feasible?: Evaluates whether the system can be developed using available technology, infrastructure, and technical skills.

- Is it financially worthwhile?: Verifies whether expected economic benefits outweigh development and operational costs.

- Are its risks acceptable?: Assesses whether project uncertainties are manageable relative to returns.

Cost-Benefit Evaluation Metrics

- Payback Period: The time required for a project to recover its initial investment from net cash inflows.

- Return on Investment (ROI): Percentage measuring project profitability relative to total investment.

- Net Present Value (NPV): Sum of discounted future net cash flows minus initial investment, accounting for the time value of money

Software Process Models

- Waterfall Model: Sequential model suitable when requirements are stable and well-understood.

- Spiral / Risk-Driven Model: Iterative model focusing heavily on risk identification and reduction in large, complex systems.

- Agile Methods: Iterative model delivering working increments rapidly when requirements change frequently

software Quality Management

Quality Frameworks & Models

- Total Quality Management (TQM): Organization-wide philosophy emphasizing customer focus, continuous process improvement, and shared quality responsibility.

- Six Sigma (DMAIC): Data-driven quality framework targeting 3.4 Defects Per Million Opportunities using Define, Measure, Analyze, Improve, and Control.

ISO 9126 Software Quality Characteristics

- Functionality: Ability to provide functions satisfying stated and implied needs (suitability, accuracy, security).

- Reliability: Ability to maintain required performance levels without failure under specified conditions.

- Usability: Ease with which users can understand, learn, and operate the system.

- Efficiency: Response time and performance relative to consumed system resources.

- Maintainability: Ease of analyzing, modifying, correcting, or enhancing code.

- Portability: Ease of transferring software to another operating environment.

Walker Royce's 7 Core Metrics

- Work and Progress: Tracks completed deliverables against planned milestones.

- Budgeted Cost: Compares planned expenditures against actual spending.

- Staffing Dynamics: Monitors headcount and team composition shifts over time.

- Change Traffic: Measures the volume and rate of requirement or artifact modifications.

- Breakage: Tracks defects, failures, or damage introduced during development.

- Rework: Measures effort spent redoing or correcting completed work.

- MTBF / Maturity: Evaluates system reliability using Mean Time Between Failures.

Risk Management

3 Categories of Risk

- Project Risks: Threats affecting management, schedules, budgets, staffing, and resources.

- Product / Technical Risks: Threats affecting software quality, architecture, security, performance, or third-party components.

- Business Risks: External commercial threats such as competitor releases, lost funding, or changing market demands.

4 Threat Response Strategies

- Risk Avoidance: Changing project scope or approach to eliminate the risk completely.

- Risk Mitigation: Taking proactive steps to reduce the probability or impact severity of a risk.

- Risk Transfer: Shifting financial impact or ownership to a third party (e.g., outsourcing, insurance).

- Risk Acceptance: Acknowledging the risk without proactive changes while establishing contingency buffers.

WBS Rules & Decomposition Styles

- 100% Rule: The WBS must encompass 100% of the work defined by the project scope—no extra work included and no required work omitted.

- Mutual Exclusion: Each WBS element must represent distinct work to avoid double-counting tasks.

- Work Package: The lowest WBS level where work can be estimated, scheduled, assigned, and monitored.

- Product-Oriented WBS: Decomposes work by major software components (e.g., User Interface, Database, Server).

- Process-Oriented WBS: Decomposes work by development phases (e.g., Requirements, Design, Coding, Testing).

- Hybrid WBS: Combines product deliverables at one level and process activities at another.

Software vs. Traditional Engineering Projects

- Invisibility: Software progress is abstract until runnable builds exist, whereas physical progress in civil or mechanical projects is directly visible.

- Conformity: Software must adapt to legacy hardware and existing software environments rather than being governed by uniform physical laws.

- Complexity: Software features high logical complexity per unit cost without standardized, repeated physical parts.

- Flexibility: Software can be modified infinitely, whereas physical materials are expensive and difficult to modify once constructed.

6 Characteristics of Software Projects

- Intangibility: Software is not a physical product and exists primarily as logical artifacts such as requirements, designs, and code.

- High Complexity: Software consists of numerous interconnected modules where a minor modification can trigger unforeseen side effects.

- Changing Requirements: Requirements evolve continuously as clients refine their needs or business conditions shift.

- High Flexibility: Software is malleable and easy to alter, which frequently encourages unmonitored scope changes.

- Difficult Progress Measurement: Development lacks physical progress indicators and must be evaluated through completed deliverables, tested features, and defect status.

- Human-Intensive: Heavily reliant on skilled personnel whose domain knowledge, communication, and teamwork dictate project success

The 9 Key Risk Identification Techniques

- Brainstorming: Project team members and stakeholders collaborate to discuss and surface potential risks based on their collective knowledge and experience.

- Checklists: Referencing standard lists of risks encountered in previous projects to check if similar threats apply to the current project.

- SWOT Analysis: Examining project Strengths, Weaknesses, Opportunities, and Threats to uncover latent risks and opportunities.

- Historical Information: Reviewing documentation, logs, and postmortem records from past projects to identify recurring problems.

- Expert Judgment: Consulting subject-matter experts who leverage specialized domain experience to spot non-obvious risks.

- Delphi Technique: Requesting independent, anonymous risk identification and evaluation from a panel of experts over multiple iterative rounds to reach consensus without personal bias.

- Scenario Analysis: Considering hypothetical future events—such as unexpected key staff resignations, server failures, or major requirement changes—to evaluate potential impacts.

- Cause-and-Effect Analysis: Tracing potential root causes to their downstream consequences to discover hidden risk sources.

- Document Analysis: Thoroughly reviewing project contracts, schedules, budgets, requirements, and architectural specifications to identify gaps or conflicting assumptions.

The Software Project Management (SPM) process spans five fundamental management process groups:

1. Initiating Phase (Feasibility & Charter)

The Initiating phase focuses on evaluating whether a software project is worth undertaking before committing financial capital and human resources.

- Strategic & Technical Assessment: Verifies that the project supports long-term business goals and competitive strategy, while ensuring the organization possesses or can acquire the necessary technology, infrastructure, and technical skills.

- Cost-Benefit Analysis (CBA) & Cash Flow Forecasting: Compares expected development and operational costs against anticipated financial benefits using financial metrics like Payback Period, Return on Investment (ROI), and Net Present Value (NPV).

- Initial Risk Assessment: Identifies high-level uncertainties regarding technology, market, and resources.

- Project Charter: Formally authorizes the project, establishes its core objectives, and defines overarching constraints.

2. Planning Phase (WBS, Schedule, Budget & Strategy)

The Planning phase converts broad project objectives into detailed, actionable operational blueprints.

- Work Breakdown Structure (WBS): Decomposes the total project scope into manageable deliverables and work packages using product-oriented, process-oriented, or hybrid styles while obeying the 100% rule.

- Software Effort & Cost Estimation: Predicts required effort (in Person-Months) and duration using structural methods (Expert Judgment, Analogy, Top-Down, Bottom-Up) or parametric models (Function Point Analysis, COCOMO).

- Activity Sequencing & Scheduling: Defines logical task dependencies (FS, SS, FF, SF), constructs network diagrams (PDM/AON or ADM/AOA), calculates activity floats, and identifies the Critical Path.

- Scheduling Methods & Schedule Compression: Employs deterministic (CPM) or probabilistic 3-time-estimate methods (PERT). If deadlines are tight, schedule compression techniques like Crashing (adding resources) or Fast Tracking (parallelizing sequential tasks) are applied.

- Process Model & Technology Selection: Chooses an appropriate lifecycle model (Waterfall, Agile, or Spiral/Risk-Driven) and tech stack.

- Risk, Quality & SCM Planning: Establishes the Risk Register and threat response strategies (Avoidance, Mitigation, Transfer, Acceptance), sets Quality Assurance (SQA) standards, and establishes Software Configuration Management (SCM) baselines.

3. Executing Phase (Development & Implementation)

In the Executing phase, the software development team carries out the planned activities to build, test, and integrate the logical components.

- Software Synthesis & Coding: Developers write, document, and integrate code modules according to architectural requirements.

- Verification & Quality Assurance: Conducts peer code reviews, inspections, unit testing, and integration testing to detect defects early.

- SCM Check-out & Modification: Developers check out configuration items (CIs) from the repository, implement approved changes, perform developer testing, and check items back in.

- Leadership & Team Direction: Allocates responsibilities according to capabilities, handles interpersonal conflicts, and maintains team motivation and coordination.

4. Monitoring & Controlling Phase (Tracking & Variance Management)

Running in parallel with execution, this phase tracks project velocity, measures deviations from baselines, and applies corrective actions.

- Schedule & Progress Control: Tracks activity completion, milestone status, and critical path dependencies.

- Configuration Change Control: Processes formal Change Requests (CRs). The Configuration Control Board (CCB) conducts impact analysis on cost, schedule, and quality before approving or rejecting scope modifications.

- Risk Monitoring: Tracks risk triggers, monitors changing probabilities/impacts, and executes contingency plans.

- Quality & Performance Metrics: Evaluates project health using core metrics like Walker Royce's 7 metrics (Work & Progress, Budgeted Cost, Staffing Dynamics, Change Traffic, Breakage, Rework, and MTBF/Maturity).

5. Closing Phase (Handover & Postmortem)

The Closing phase brings the software project to a formal and orderly conclusion.

- Client Handover & Acceptance: Conducts acceptance testing alongside Functional Configuration Audits (FCA) and Physical Configuration Audits (PCA) to verify that the final deliverable matches all approved requirements and documentation.

- Administrative Closure: Finalizes financial accounts, closes vendor contracts, and releases project staff and resources.

- Postmortem Evaluation & Lessons Learned: Documents project performance, estimation accuracy, and team feedback in historical archives to improve future project planning.

Software Configuration Management

The 4 Elements of SCM

- Configuration Identification: Defining and uniquely labeling Configuration Items (CIs) and baselines.

- Configuration Change Control: Evaluating, approving, and recording modifications formally via a Configuration Control Board (CCB).

- Configuration Status Accounting: Maintaining logs of who changed what, when, why, and which version is active.

- Configuration Audit: Conducting Functional (FCA) and Physical (PCA) audits to verify compliance with approved baselines.

The 6-Step SCM Change Control Workflow

- Change Request (CR): Stakeholder formally submits a document describing a proposed modification.

- CCB Evaluation & Impact Analysis: CCB analyzes impacts on cost, schedule, security, and dependent CIs.

- CCB Approval or Rejection: CCB formally approves, rejects, or defers the change request.

- Check-out & Code Modification: Developer checks out the CI, implements changes, and performs developer testing.

- Review, Testing & Audit: Code undergoes peer review, regression testing, and verification audits.

- Check-in & Baseline Update: Modified CI is checked back in, and the official baseline moves forward.

Version Control System Architectures

- CVS: Centralized system with file-by-file commits (non-atomic), heavy branching, and required server connectivity.

- SVN: Centralized system featuring atomic commits and versioned directories, but dependent on a central server for operations.

- Git: Distributed system providing full local repository copies on every client, lightweight branching, and full offline operations.